## 18
S.No | Tickets | Issue | Assignee | Estimation in Hours | % Completion | %Pending | TimeTaken |  |  |  | Production_Time_Taken
1 |  | No of Payment Terms dropdown with '+' button ,Should dedit in the payslip based on the terms (with numbers eg.1/20) | Ajith | 16 | 90 | 10 | 24 | 0.26667 | 2.6667 | -8 | -10.6667
|  | Login Page Design and Modifications |  | 2 | 90 | 10 | 1 | 0.011111 | 0.11111 | 1 | 0.88889
|  | Filter - Vendor,Customer, HR, Bank, Tax,Mange User (15) |  | 10 | 70 | 30 | 10 | 0.14286 | 4.2857 | 0 | -4.2857
2 |  | Expense History | Surya | 6 | 100 | 0 | 3 | 0.03 | 0 | 3 | 3
|  | Discussion with Srini Sir |  |  |  |  | 3 | #DIV/0! | #DIV/0! | -3
|  | HR Tool Kit |  | 6 | 90 | 10 | 4 | 0.044444 | 0.44444 | 2 | 1.5556
3 |  | Employee Info -> Create Employee | Madhu | 6 | 100 | 0 | 9 | 0.09 | 0 | -3 | -3
|  | Email |  | 4 | 80 | 20 | 5 | 0.0625 | 1.25 | -1 | -2.25
|  |  |  | 24 | 90 | 10
|  | 16 | 90 | 10

## Sep4
S.No | Issue | Assignee | % Completion | %Pending | TimeTaken |  |  |  | Production_Time_Taken
1 | Csv Upload serviceProvider | Ajith | 100 | 0 | 2 | 0.02 | 0 | #REF! | #REF!
| Vendor Previous balance |  | 100 | 0 | 1 | 0.01 | 0 | #REF! | #REF!
| Upload Expenses Details |  | 10 | 90 | 5 | 0.5 | 45 | #REF! | #REF!
2 | Natwestern Designs & Flow Chart | Madhu |  |  | 5
| Vendor Expense - Migration - Stockeai |  |  |  | 3
3 | Natwest Documentation | Surya | 50 | 50 | 2
| Migration - Stockeai |  | 10 | 90 | 6

## 17
S.No | Tickets | Tickets | Issue | Assignee | Estimation in Hours | % Completion | %Pending | TimeTaken |  |  |  | Production_Time_Taken | Work Done
1 |  | SR-2 | Grand total(Preferred currency), Amount paid & Balance amount - Decimal error/ Supplier Ledger | Surya |  |  |  | 3 | #DIV/0! | #DIV/0! | -3
|  | SR-3 | Index page filter fixes |  |  |  |  | 2
|  |  | Natwestern Meeting |  |  |  |  | 1
|  |  | Stockeai -discussion |  |  |  |  | 1
2 | Ticket no:18 | SR-1 | Index page filter fixes / CodeMerge live | Madhu | 10 | 100 | 0 | 17 | 0.17 | 0 | -7 | -7
|  | SR-3 | Natwestern Meeting |  |  |  |  | 1 | #DIV/0! | #DIV/0! | -1
3 |  | SR-8 | Custome and Vendor page - To fix errors while currency is displayed | Ajith | 4 | 100 | 0 | 6 | 0.06 | 0 | -2 | -2
|  |  | Sale /Expense Manage Page (Row per Page ) |  |  |  |  | 1
S.No | Tickets | Tickets | Issue | Assignee | Estimation in Hours | % Completion | %Pending | TimeTaken |  |  |  | Production_Time_Taken | Work Done
1 |  | STOC-4 | Changes in Settings Menu | Ajith | 6 | 100 | 0 | 7 | 0.07 | 0 | -1 | -1
|  | STOC-2 | Vendor - Manage and Ledger Page |  | 1.5 | 100 | 0 | 2
|  |  | Bug Fixes |  |  |  |  | 1
2 |  | STOC-6 | Payment History ticket | Surya | 16 | 40 | 60 | 8.5 | 0.2125 | 12.75 | 7.5 | -5.25
|  |  | PPT - Sales Meeting |  |  |  |  | 45min
3 | Ticket no:18 | STOC-9 | Payment - Manual Payment , File Upload-Creation | Madhu |  |  | 15 | 8 | #DIV/0! | #DIV/0! | -8 | 1
S.No | Tickets | Tickets | Issue | Assignee | Estimation in Hours | % Completion | %Pending | TimeTaken |  |  |  | Production_Time_Taken
1 |  |  | Quick Book -Report / Stockeai Report -To check | Ajith |  |  |  | 2 | #DIV/0! | #DIV/0! | -2 | #DIV/0!
|  |  | Sales (Tax Isssue / Remove Product Name -On Focus ) |  |  |  |  | 2
|  |  | Expense(Index Page code Mege / Remove Product Name -On Focus ) |  |  |  |  | 2
|  |  | Sales (rows per page / Fillter by search aligment issue) |  |  |  |  | 1
|  |  | Service Provider -create/edit ( aligment issue) |  |  |  |  | 1
2 |  | STOC-6 | Payment History ticket | Surya | 16 | 70 | 30 | 20.5 | 0.29286 | 8.7857 | -4.5 | -13.2857
|  |  | Discussion with Srini Sri |  |  |  |  | 1
3 | Ticket no:18 |  | Nast west functionalities | Madhu |  | 85 | 15 | 8 | 0.094118 | 1.4118 | -8
|  |  | Testing -Invoice Pdf | susmitha |  |  |  | 8
S.No | Tickets | Tickets | Issue | Assignee | Estimation in Hours | % Completion | %Pending | TimeTaken
1 |  |  | Sales /Expenses colors issue -10 pdf (Print color id on top ) | Ajith |  | 100 | 0 | 6
|  |  | Sales/Expenses Pdf (logo issue-Quote/Ocean Import ) Header aligment issue all pdf |  |  | 30 | 70 | 2
2 |  | STOC-6 | Payment History ticket | Surya | 16 | 90 | 10 | 27
|  |  | Discussion with Srini Sri |  |  |  |  | 1
3 | Ticket no:18 |  | Training |  |  |  |  | 30min
|  |  | Testing -Invoice Pdf | susmitha |  |  |  | 8
S.No | Tickets | Tickets | Issue | Assignee | Estimation in Hours | % Completion | %Pending | TimeTaken
1 |  |  | Disucssion about Stockeai | Surya |  |  |  | 1
|  | STOC-6 | Payment History ticket |  | 16 | 90 | 10 | 24 | 0.26667 | 2.6667 | -8 | -10.6667 |  | -11
2 |  |  | Sales/Expenses Pdf Header aligment issue all pdf (template -1/template -2) | Ajith |  | 50 | 50 | 7
| Ticket no:18 |  | Disucssion about Stockeai |  |  |  |  | 1
3 |  |  | Testing -(Invoice Pdf/aligment issue) | susmitha |  |  |  | 7
|  |  | Disucssion about Stockeai |  |  |  |  | 1
4 |  |  | Testing | Jaishree |  |  |  | 5
S.No | Tickets | Tickets | Issue | Assignee | Estimation in Hours | % Completion | %Pending | TimeTaken
1 |  |  | Report Pdf , Excel and print | Surya | 9 | 30 | 70
|  |  | R25 , 26,27 Tickets Discussion with srini sir |  |  |  |  | 1.5
|  |  | Supplier Ledger issue cleared |  |  |  |  | 0.5
|  |  | Data Migration (Quickbook and Stockeai )- Count - Checked |  |  |  |  | 0.5
|  |  | Account Category and Sub Category Passing Service Provider Data |  |  |  |  | 1.5
2 |  |  | sales /Expenses Design (Create /Edit ) | Ajith | 16 | 40 | 60 | 6.5
| Ticket no:18 |  | Data Migration (Quickbook and Stockeai )- Count - Checked |  |  |  |  | 45min
3 |  |  | Disucssion -Pdf / Template Design |  |  |  |  | 45min
S.No | Tickets | Tickets | Issue | Assignee | Estimation in Hours | % Completion | %Pending | TimeTaken |  |  |  | Production_Time_Taken
1 |  |  | Pdf design | Surya | 8 | 50 | 50 | 5 | 0.1 | 5 | 3 | -2
|  |  | Natwest PPT presentation |  |  |  |  | 1.5
|  |  | Team Meeting |  |  |  |  | 0.5
2 |  |  | Stockeai Overall Dynamic Color | Ajith | 10 | 60 | 40 | 13 | 0.21667 | 8.6667 | -3 | -11.6667
|  |  | Team Meeting |  |  |  |  | 0.5
3 |  |  | Setting Notification sales & expense | Madhu | 12 | 60 | 40 | 7 |  |  |  | 0
|  |  | Natwest PPT presentation |  |  |  |  | 1
4 |  |  | Infinity stones migration | Susmitha | 14 | 80 | 20 | 12.5 | 0.15625 | 3.125 | 1.5 | -1.625
|  |  | Digital marketing- MSME website |  |  |  |  | 1
|  |  | Competitor Analysis |  |  |  |  | 1
|  |  | Team Meeting |  |  |  |  | 0.5
S.No | Tickets | Tickets | Issue | Assignee | Estimation in Hours | % Completion | %Pending | TimeTaken |  |  |  | Production_Time_Taken
1 |  |  | Pdf design | Surya | 8 | 50 | 50 | 5 | 0.1 | 5 | 3 | -2
|  |  | Natwest PPT presentation |  |  |  |  | 1.5
|  |  | Team Meeting |  |  |  |  | 0.5
2 |  |  | Website ads Video creating | Ajith |  |  |  | 2.5 | #DIV/0! | #DIV/0! | -2.5 | #DIV/0!
|  |  | R29 Estimation |  |  |  |  | 0.5
|  |  | Team Discussion |  |  |  |  | 0.5
|  |  | Payment history --> If the distributed amount exceeds the amount to pay value,then show the balance amount in the field named as 'Advance' |  | 4 | 80 | 20 | 4.5 | 0.05625 | 1.125 | -0.5 | -1.625
3 |  |  | Create a calendar page to scheduled a task and the notifications also should add on the respective date if they selected as calendar in the source | Madhu | 14 | 80 | 20 | 12.5 | 0.15625 | 3.125 | 1.5 | -1.625
|  |  | Hores Logo Creation / Diwali Posters creation |  |  |  |  | 1
4 |  |  | R28 Testing | Susmitha |  |  |  | 3 | #DIV/0! | #DIV/0! | -3 | #DIV/0!
|  |  | collect and create new Invoices (Sales) - STONEMART |  |  |  |  | 5

## Sheet1
S.No | Issue | Assignee | % Completion | %Pending | TimeTaken
1 |  | Surya | 100 | 0 | 4
| Estimation Of R22 Tickets |  | 100 | 0 | 1
| React and Node js installation and research on google about the server connections |  |  |  | 2
2 | Stone Mart Migration Upload Supplier Expense | Madhu |  |  | 3
| Designing on NatWest as last meeting Discussion |  |  |  | 5
3 | Service provider | Ajith |  |  | 5
| Testing |  |  |  | 2.5

## Sheet2
S.No | Tickets | Tickets | Issue | Assignee | Estimation in Hours | % Completion | %Pending | TimeTaken |  |  |  | Production_Time_Taken
1 |  | SR-9 | Add field Past Due - In the Ledger Page we have Past due date when the Payment due date exceeds , the Past Due field in the Manage page should contain the sum amount of payment pending which has the number of days in the past due | Surya | 4 | 44 | 4 | 2 | 0.045455 | 0.18182 | 2 | 1.8182
|  | SR-11 | Documentation- Stockeai - Data Migration |  | 5 | 100 | 0 | 8
|  | SR-3 | Rows Per Page , Search options ,Column Selections should not change on Page Refresh |  |  |  |  | 2
|  | SR-6 | Rename Outstanding Field Name to Open Balance. Show Past due Date only when there is a due amount |  | 2 | 100 | 0 | 1 | 0.01 | 0 | 1 | 1
2 | Ticket no:18 | SR-1 | While creation and Edition, on click submit button should check with database whether the Product with the same model and Price is already available.If yes,A popup should show as " Product Name with same Model and Sales Price is Available" (with Ok button).If ckick OK.The Popup should hide. | Madhu | 5 | 100 | 0 | 3 | 0.03 | 0 | 2 | 2
|  | SR-3 | Rows Per Page , Search options ,Column Selections should not change on Page Refresh |  | 10 | 70 | 30 | 10 | 0.14286 | 4.2857 | 0 | -4.2857
3 |  | SR-7 | Customer and Vendor id- issue to be fixed | Ajith | 1 | 100 | 0 | 1 | 0.01 | 0 | 0 | 0
|  |  | Rearrang all buttons and icons in the index page |  | 6 | 100 | 0 | 6
|  |  | Code merge / testing |  |  |  |  | 1

## Sheet3
S.No | Tickets | Issue | Assignee | Estimation in Hours | % Completion | %Pending | TimeTaken |  |  |  | Production_Time_Taken
1 |  | Time Tracker ,fond solution in Jira | Surya |  |  |  | 30mins | #VALUE! | #VALUE! | #VALUE!
| R23 | Sales Bug Fixes |  |  |  |  | 5
| STOC-6 | Payment History |  | 16 | 20 | 80 | 2 | 0.1 | 8 | 14 | 6
2 | STOC-9 | System Audit | Madhu | 3 | 100 | 0 | 4 | 0.04 | 0 | -1 | -1
| STOC-11 | Payment - Manual Payment , File Upload-Creation |  | 16 | 60 | 40 | 4 | 0.066667 | 2.6667 | 12
3 | STOC-1 | Index Page - Advanced Search Button | Ajith | 1.5 | 100 | 0 | 1.5 | 0.015 | 0 | 0 | 0
| STOC-2 | Vendor - Manage and Ledger Page |  | 1 | 70 | 30 | 1.5 | 0.021429 | 0.64286 | -0.5 | -1.1429
| R23 | BUG FIXES |  |  |  |  | 5